# Early Learning Council Strategic Planning Timeline

Throughout 2018, the majority of the Council’s work will be engaging cross-sector partners to inform the creation of an updated Strategic Plan. As such, several meetings will primarily be dedicated to this engagement, with 3-4 hours for the first part of each meeting dedicated to engagement sessions and approximately 2 hours dedicated to Council business. *\*K-12, Human Services & Health may be rearranged for scheduling purposes\**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **October 2017** | **November 2017** | **January 25, 2018** | **February 22nd**  3 Hour Session | **March 22nd**  4 Hour Session | **April 26th**  4 Hour Session | **May 24th**  4 Hour Session | **June 22nd**  1 Hour Session | **July**  ***No ELC Meeting*** | **August *No ELC Meeting*** | **September 27th** | **October 24-25th** | **November 15th** |
| *Maternal Child Health Update (OHA)* | *COSA Panel* | *Finalize input on Governor’s Priorities* | **Early Learning Engagement Session**  -Early Learning Funders Circle (identify partners) | **Debrief Early Learning Engagement Session (1 hr)** | **Debrief Health Engagement Session (1 hr)** | **Debrief K-12 Engagement Session (1 hr)** | **Debrief Human Services Engagement Session (1 hr)** |  |  | Revisit Goals and Legislative Strategies with Agency Directors | **Early Learning Council Retreat:** Review Final-Draft Strategic Plan | Adopt ELC Strategic Plan |
|  |  |  |  | **Health Engagement Session (3 hrs)**  -OHA, OHPB  -Community Partners  -Hubs (with Parents & Families)  -Advocates & Philanthropy | **K-12 Engagement Session (3 hrs)**  -ODE, SBE  -Community Partners  -Hubs (with Parents & Families)  -Advocates & Philanthropy | **Human Services Engagement Session (3 hrs)**  - DHS/Self Sufficiency  -Community Partners  -Hubs (with Parents & Families)  -Advocates & Philanthropy | Ongoing Summer: Community Engagement  -parents  -provider  -CBOs  -business leaders  Support from BUILD?  -interviews with business leaders  -develop protocols for focus groups with parents, providers | | |  |  |  |
| **Outside Engagements** |  |  | **February 7th** Hub Collaborative *How much time is needed?* | **Date TBD**  G2G Ed Cluster |  |  | **Dates TBD**  -Summer Hub Collaborative;  -Governor’s Ed Cabinet | | |  | Updated: December 15, 2017 |  |